# **BP1 Deliverables Status**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Completion/Due Date** | **Sub-Awardee** | | **Deliverable** | **Activity #** | **Status** |
| **LHDs** | **Tribes** |
| 3/12/2020 | X |  | MISNS SharePoint Training - participation | 15.1 | Cancelled |
| 3/18/2020 | X |  | MISNS Request SharePoint Drill - Option A | 15.2 | Cancelled |
| 3/31/2020 |  | X | Updated EOP | 9.1 | Moved to BP2 |
| 3/31/2020 | X |  | Q3 IMATS Drill | 17.1 | Cancelled |
| 3/31/2020 | X |  | Q3 WCI progress report and supporting documentation | 19.1 | Cancelled |
| 5/5/2020 |  | X | Attendance at GLHSC (Optional, but highly encouraged) | 11.1 | Cancelled |
| 6/30/2020 | X | X | NIMS Training Compliance form | 2.1 | Due August 24 |
| 6/30/2020 | X | X | Staff Assembly exercise/documentation | 5.1 | Due August 24 |
| 6/30/2020 | X |  | TEPW documentation | 14.1 | Due August 24 |
| 6/30/2020 | X |  | Participation in two (2) MICIMS exercises, no submission | 20.1, 20.2, and 20.3 | Cancelled |
| 6/30/2020 | X |  | Q4 IMATS Drill | 17.1 | Cancelled |
| 6/30/2020 | X |  | Q4 WCI progress report and supporting documentation | 19.1 | Cancelled |
| 7/31/2020 | X | X | End-of-Year Progress Report |  | Due August 24 |
| 7/31/2020 |  | X | Participation in LHD or HCC exercise, submit Exercise Participation Report | 12.1 | Completed  (COVID-19 pandemic) |
| Mid and EOY PR | X | X | AAR/IP for any exercise conducted, incident or planned event | 3.1 | Due August 24 |
| Mid and EOY PR | X |  | Annual Volunteer Notification Drill - AAR submission | 18.1 | Cancelled |
| Monthly |  | X | Attendance at Regional HCC meetings | 10.1 | Cancelled |
| Quarterly | X | X | BETP 800 MHz Radio Testing, quarterly participation | 4.1 | Cancelled |
| TBD | X | X | CPG Assessment Tool (released by CDC in late Fall) | 7.1 and 7.2 | Completed |
| w/Mid and EOY Report | X | X | LHD-Tribe MOU/MOA Review | 6.1 | Moved to BP2 |